## Product Backlog
[Group Number and members]
[Project title]
Product Backlog | [5 empty] | Use index colors to show revisions on task time
Unique ID | Task | Sprint | Estimated time (minutes) | Time after Iteration 1 | Time after Iteration 2 | Index | Information
Target Time
1 | Plan and Design |  | 560 | 0 | 0 |  | Revised Target Time
1.01 | Research YOLOv5 implementation | 1 | 60 |  |  |  | Actual Time Taken
1.02 | Study OpenCV algorithms and integration | 1 | 60 |  |  |  | New Task Added
1.03 | Build the directory structure | 1 | 30
1.04 | Write CMakeLists.txt files | 1 | 30
1.05 | Write dummy test cases | 1 | 60
1.06 | Write the implementation stub for detector | 1 | 30
1.07 | Write the implementation stub for tracker | 1 | 30
1.08 | Write the Doxygen documentation | 1 | 30
1.09 | Ensure Google C++ styling | 1 | 10
1.1 | Update Readme with build instructions | 1 | 30
1.11 | Revise UML diagrams | 1 | 60
1.12 | Setup GitHub repo, CI and code coverage | 1 | 60
1.13 | Push code base into repository | 1 | 10
1.14 | Discuss future implementation steps | 1 | 60
2 | Implementation |  | 560 | 0 | 0
2.01 | Implement the class methods for detector | 2 | 90
2.02 | Implement the class methods for tracker | 2 | 90
2.03 | Implement OpenCV transform methods to get coordinates | 2 | 60
2.04 | Update CMakeLists.txt files | 2 | 30
2.05 | Implement proper unit tests | 2 | 90
2.06 | Perform debugging and error fixing | 2 | 60
2.07 | Update Doxygen comments | 2 | 10
2.08 | Update UML diagrams | 2 | 30
2.09 | Ensure GitHub CI works for all test cases | 2 | 30
2.1 | Test for code coverage | 2 | 30
2.11 | Ensure final Google C++ styling | 2 | 10
2.12 | Final Readme update | 2 | 30
Remaining effort
| Total effort time |  | 1120

## Iteration backlog - 1
[Group Number and members]
[Project title]
Iteration Backlog 1
Unique ID | Task | Target time (minutes) | Actual Time | Status
1 | Plan and Design | 0 | 0

## Iteration backlog - 2
[Group Number and members]
[Project title]
Iteration Backlog 2
Unique ID | Task | Target time (minutes) | Actual Time | Status
2 | Implementation | 0 | 0

## Work log
[Group Number and members]
[Project title]
Work/ Time log
Process Enactment |  | Pair Programming Roles | [5 empty] | Interrupt
Task / Step | Comment | Driver | Navigator | Design Keeper | Date | Start | End | # | Time | Clean time
Iteration 1
[11 empty] | Task / Step | Meaning
[11 empty] | Pri | backlog prioritization
[11 empty] | Div | dividing the change into smaller parts
[11 empty] | Ini | software change initiation
[11 empty] | CL | concept location
[11 empty] | IA | impact analysis
[11 empty] | Ref | refactoring and testing
[11 empty] | Act | actualization and testing
[11 empty] | Test | other testing
[11 empty] | Bas | baseline build
[11 empty] | Rel | release
Iteration 2 | [10 empty] | Ex | exceptional task or phase